## Slide 1
PowerPoint 1: How projects are defined and structured
17. Project and programme management
17.1 Principles of project management

## Slide 2: Objectives
By the end of this session learners should be able to:
explain how projects are defined and structured, including
  the project brief
  the project goals
  the success criteria.

## Slide 3: What is a project?
Examples of projects in engineering and manufacturing include constructing a bridge, bringing a new car model to market or setting up a new manufacturing line.
All projects have a beginning and an end.
They have a team, a budget, a schedule and a set of expectations the team needs to meet.
Projects are distinct from the ongoing day-to-day activities of an organisation, because they reach a conclusion once the goal is achieved.

## Slide 4: Why is project management important?
Nearly all organisations will carry out projects of one kind or another, meaning that in the workplace project management skills are highly valued. Project and programme management ensure that projects run smoothly and meet expectations.

## Slide 5: How projects are structured
Projects have a set time span with a beginning and an end.
A project life cycle structures the project into stages. Each stage involves different sets of activities.
Before a project begins, there is a pre-planning stage, during which the project brief, goals and success criteria are set out and defined.
Initiation
Planning
Implementation
Monitoring
Reporting
Evaluation

## Slide 6: Project brief
To ensure success, a new project should have a clear, detailed and explicit project brief. A project brief will vary from organisation to organisation, however it should contain key pieces of information, such as:
project goals/objectives: the central aims of the project
deliverables: what should be delivered at the end of the project
timeline: a final completion date, with milestone dates for key stages
budget: the financial constraints of the project
success criteria: how the project will be judged to have been successful.

## Slide 7: Describing a swing
Try describing a child’s swing:
  without using the word ‘swing’ (no word exists for it as yet)
  without drawing a swing (no one has ever seen one)
  without explaining how to make one.
  Share your notes with the rest of the group. How successful is your attempt at a description? On the next slide you will see how a single concept can be interpreted (or misinterpreted) in numerous ways. Without a clear project brief, there is a danger that the end product may fulfil its essential function but be a long way from the conception held by a client.

## Slide 8: Interpretations of an idea

## Slide 9
In industry, what is needed can sometimes be hard to capture in a brief without first asking:
Does the customer know what they want?
Identifying customer needs and agreeing how the project will meet these needs is a crucial first step in setting a project brief. Not all projects are designed for external customers. A company may set itself a project. For example, to reduce manufacturing costs, roll out new software, improve a manufacturing process and so on.
The principle of identifying needs is no different: internal customers’ needs should be treated in the same way as external customers. All projects must to delivered to meet criteria set by the business.
Identifying needs

## Slide 10
One way of approaching a project brief is to focus on a particular problem.
What problem are we trying to solve?
Designers and engineers can get carried away with wonderful technology, the challenges of the design and the possibilities of producing something really innovative and interesting. This leads naturally to the questions What? and How?
What are we delivering? How will we build it?
Before focusing on What? and How?, it is worth taking the time to consider:
Who? Where? Why? When?
Project brief

## Slide 11: Swinging again
Asking yourself who, where, why, when, what and how, rewrite your description of the swing.
Who will use it?
Where will it be located?
Discuss any significant changes that emerge.
You should now have a more detailed and informative description: a very basic brief.

## Slide 12: Writing a brief
Creating a project brief should be an iterative process.
It may require the stakeholders of the project (eg customer, designer, manufacturer) to have several conversations to capture the details. Communication is key.
Getting the brief right at the start will set clear project expectations. One important question to ask when setting expectations in a brief is: How can we tell when a project is finished?
Project goals and success criteria need to be included in the brief. When these are met, the project can be considered complete.

## Slide 13: What are project goals?
Project goals are usually high level, broad aims that a project sets out to achieve. Project goals should be SMART:
Specific, Measurable, Achievable, Realistic, Timely
For example, a project to refine an electric car battery design might include goals such as:
reduce battery weight by 2%
reduce time taken to manufacture batteries by 0.5 days per unit
achieve sustainability targets by increasing recyclable materials by 5%.

## Slide 14: Success criteria
Success criteria enable project managers to identify what project success should look like. These criteria should be agreed with project stakeholders (eg customers) so everyone can answer the question:
What criteria must the project meet for it to be considered successful?
Examples might include:
the project delivers all deliverables within the agreed scope
the project achieves agreed customer satisfaction targets
the project handover was completed to the agreed time frame with proper documentation and training provided.

## Slide 15: Project brief example
Project outcome: a prototype unit is delivered to the museum for testing no later than 12 weeks after the beginning of the project. The unit will satisfy all requirements outlined in the brief.
Success criteria: the unit passes all fair tests and is delivered as required (eg to time and within budget).
Project brief: a free-standing hand sanitising unit suitable for use by all visitors to a museum. The unit must work without the need for visitors to touch any part of the unit with their hands.

## Slide 16: Agreeing the project brief
Assuming the project brief is clear, detailed and explicit, what happens now?
Once both sides have agreed the brief, it becomes a contract between them.
Any changes will need renegotiating and might cost the customer more money or time.

## Slide 17
Any questions?
‘T-LEVELS’ is a registered trade mark of the Department for Education. ‘T Level’ is a registered trade mark of the Institute for Apprenticeships and Technical Education.