## Slide 1
PowerPoint 2: Project life cycle
17. Project and programme management
17.1 Principles of project management

## Slide 2: Objectives
By the end of this session learners should be able to:
describe the various management practices, processes and documentation needed at each stage of a project
outline in detail a typical project life cycle.
Initiation
Planning
Implementation
Monitoring
Evaluation
Reporting

## Slide 3: Project initiation
At the start of a project great care must be taken. It is easy to charge into the interesting stages without making sure everything is ‘good to go’. Your project brief should have identified:
why – the project’s goals and purpose
what – the project’s scope, including your budget
who – key stakeholders and project team members.
Your goals and success criteria should be agreed.
Typically, at the start of a project, a meeting is called with representatives of all stakeholders present (eg those who will approve the project, its budget and resources). This gives the best chance of nothing major being forgotten.

## Slide 4: Case example
There may be information available that can impact on the project but no one at the meeting knows anything about it.
A company has been asked by a customer to make an injection moulded seal for a water pump. The production representative was not at the project initiation meeting. The company designs the seal but, when the time comes to make a batch, the production department says the required production equipment is undergoing scheduled maintenance and cannot be put to use in time.
The customer has to get the seals made by another company and spend much more money in the process.

## Slide 5: Agile management techniques
One way to avoid situations such as this is by using agile management techniques such as failure mode and effect analysis (FMEA), which can cover process, production, design and so on.
All relevant departments send a representative to a meeting where they try and think of all the things that could go wrong.
This a powerful tool because it acts as a reminder for people not to assume things will be fine when there is a chance they may not be.

## Slide 6: Planning phase
The next stage in the project life cycle is the planning phase. This includes the following activities.
Using the project brief to write a more detailed project plan – a blueprint for how the project will be delivered.
Detailing the scope and budget of the project.
Setting deadlines and milestones.
Identifying team roles and responsibilities.
Choosing the tools for planning and managing the project.

## Slide 7: Time and resources
Planning will often will take the form of a Gantt chart. Such charts assist in planning activities against the available time and resources. Where ‘it’ represent an end product, the resources include:
  Staff
  Materials
  Machinery
  Factory space
  Storage
  Someone to make it
  Something to make it out of
  Something to make it with
  Somewhere to make it
  Somewhere to keep it

## Slide 8: Documentation
A typical project Gantt chart looks like this. Team members are assigned tasks along a timeline through to project delivery.

## Slide 9: Concluding the planning
Once a project plan has been established and documented, everyone should be aware of:
what will happen
when it will happen
who will be making it happen
what to do if there’s a problem
what the outcome should be.

## Slide 10: Implementation phase
During the implementation phase:
the project plan is put into action
the project team do the work to produce the agreed project deliverables.
The project manager oversees the activities of the project team and directs each stage of the work.

## Slide 11: Potential setbacks
So, if the project plan has been well written, implementation should be easy. Everything should run smoothly …
But, problems can still occur.
Perhaps someone new has been brought onto the job.
Another, more urgent, project starts unexpectedly.
The customer pulls out of the agreement.
If anything like this happens then the project team meet to decide what to do. No one should panic or make sudden decisions.

## Slide 12: Ongoing records
It is very important to keep minutes of all meetings, actions and outcomes. It is quite usual to keep all these documents electronically and use a software application such as Microsoft Teams to coordinate it all.
Minutes are a description of what happens in a meeting.
There is a fairly standard format that is recognised by most people.
This means that it is easy for someone to understand what was discussed or decided at the meeting.

## Slide 13: Minutes
Minutes begin with a list of all those present, including anyone on a video call, and anyone who was invited but can’t make it.
Date of meeting | 1 May 2022
Title of meeting | Project planning for new pump seal
Location of meeting | Conference room 2
Present | Cassy Powell (project manager), Andy Birchall, Azim M. Jones, Charlie Bukowski, Chaz McFly (via Teams)
Absent | Fiona Serkis – apologies received

## Slide 14: Agenda
Everything that should happen during the meeting is listed in the agenda.
Agenda Minutes of the last meeting Matters arising Project progress – design Project progress – testing Customer feedback AOB (any other business) Date of next meeting
If this is part of a series of meetings then what was recorded for the last meeting should be considered
Some people will have been given tasks to do at the last meeting. They were ‘actioned’. This looks at whether they have been done
Progress is discussed. If something needs to be done then a member of the meeting will be ‘actioned’ to do it

## Slide 15: Monitoring
As the project runs through the implementation phase, it must be monitored. Implementation and monitoring run in parallel during a project.
Project monitoring should be built into the plan. Monitoring activities might include:
tracking a project’s schedule to ensure milestones are met
monitoring spending to ensure the project stays within budget
regular meetings to check on progress and identify problems
identifying roadblocks and putting plans in place to avoid them.
Monitoring can also uncover problems that may go undetected.

## Slide 16: Communication methods
As well as meetings, companies may use email or messaging apps to communicate throughout a project.
Whatever method they choose it should be written into company procedures. The company should decide how to make sure that communication is workable and projects are well monitored.
Managers should be able to check on staff; staff must feel they can raise concerns about the project without feeling they will get into trouble. All communication should be recorded and the outcomes kept for future project teams to learn from.

## Slide 17: Reporting
Initiation
Planning
Implementation
Monitoring
Reporting
Evaluation
Reporting during the project life cycle also runs in parallel with implementation and monitoring.
Reporting should be accurate and transparent.
Project tracking tools should be kept up to date and accessible.
It is also important that the project manager reports progress to internal and external stakeholders at appropriate milestones in the project.

## Slide 18: Evaluation
All projects should be evaluated at completion to identify successes (against any set criteria) and failures.
Future projects should take both these elements into account in order to progressively improve the process.

## Slide 19
Any questions?
‘T-LEVELS’ is a registered trade mark of the Department for Education. ‘T Level’ is a registered trade mark of the Institute for Apprenticeships and Technical Education.