## Slide 1
PowerPoint 8: Gantt charts
17. Project and programme management
17.3 Project planning and control

## Slide 2: Objectives
By the end of this session learners should be able to:
understand the function and applications of Gantt charts in project and programme management.

## Slide 3
Named after Henry Gantt, an American mechanical engineer and social scientist, a Gantt chart is a horizontal bar chart used in project management to visually represent a project plan over time. A quick glance at a Gantt chart typically shows the timeline and status for each task in a project:
when each task will begin and end
how long each task will take
who is assigned to each task
how tasks relate to each other
how work is progressing in a project
the full project schedule from start to finish.
What is a Gantt chart?

## Slide 4: A simple Gantt chart
This Gantt chart shows four employees at Cavalcade Engineering working on a desk lamp project that should take seven weeks to complete.

## Slide 5: Building the detail
Once a Gantt chart has been set up, tasks should be identified and assigned to members of the team, as shown here.

## Slide 6: Keeping up to date
Gantt charts should be working documents. The important principle of planning tools such as Gantt charts is to keep them up to date.
If required, different versions should be saved in order to track the changes in a project over time. For example, should a team member fall sick, the chart would need adjusting to show which team members are taking over that person’s duties until they return.

## Slide 7: Dependent activities
What if Ziggy needs the design for the shade and base before he can order the materials to make them? What if Chloe and Jack need the design for the circuit from Fred before they can design their part of the lamp? These are called dependent activities, as one depends on the completion of another.

## Slide 8: Linked Gantt charts
Sometimes dependencies can be marked or linked on a Gantt chart. Here we can see that Jack and Chloe have to start designing before Ziggy can order the materials, and Ziggy has to check the equipment before Chloe and Jack can use it. Fred has to design the circuit very early. Tasks are typically written in boxes like this. There can be extra information in each box such as how long each task should take.

## Slide 9: Adjusting the schedule
After adjustment for dependencies, the project has extended from seven to nine weeks, but this is more realistic and Ziggy and Fred can be used on other projects when they are not busy.

## Slide 10: Pros and cons of Gantt charts
Advantages | Disadvantages
Visual, graphical way of displaying project stages. Easy to interpret with minimal training/knowledge. | Dependencies cannot be seen clearly, unless marked with vertical lines. These can make the chart cluttered and harder to interpret.
Allow tasks to be assigned and accountabilities made clear. Allow stakeholders to identify milestone dates in a schedule. Project status is clear – today is marked, and colour shading can show tasks completed. | Gantt charts can be inflexible – if something changes, a lot of revision is required to revise the chart. Gantt software has made this easier.

## Slide 11
Any questions?
‘T-LEVELS’ is a registered trade mark of the Department for Education. ‘T Level’ is a registered trade mark of the Institute for Apprenticeships and Technical Education.