## Slide 1
PowerPoint 9: CPA
17. Project and programme management
17.3 Project planning and control

## Slide 2: Objectives
By the end of this session learners should be able to:
give an overview of critical path analysis (CPA) and the associated project evaluation and review technique (PERT).
Notes: Image shows the process for building a model train set.

## Slide 3: Critical path analysis (CPA)
Critical path analysis (CPA) dates from the 1950s and is still widely used.
A critical path is a visual representation of project tasks and the time required to complete each one.
CPA is a step-by-step project management technique, used to identify activities on the critical path.
It breaks a project into work tasks using a flow chart, and calculates the project duration based on estimated time frames for each task.
It also identifies tasks that are time critical.

## Slide 4: CPA
CPA shows how tasks should be completed in the most efficient way. Each task runs from the last and depends on it.
There can be extra information in each box such as how long each task should take. CPA allows for planners to look at the order of tasks and make clear decisions.
Ziggy
Cleans laser cutter
Ziggy
Checks laser cutter
Jack
Uses laser cutter
Chloe
Uses laser cutter

## Slide 5: PERT charts
Project evaluation and review technique (PERT) is a project management planning tool used as part of CPA to calculate the how long it will take to finish a project. PERT charts are used to plan the tasks that form part or all of a project.
Nodes (shapes) are tied together with lines or arrows, together representing the sequence and completion of tasks. Arrows represent the activities, or work, necessary to reach the events (nodes) that represent each completed phase of the project.
All materials in stock
Equipment ready
Product complete
Start project
All materials ordered
Product manufactured

## Slide 6: Dependent tasks
The materials will not be in stock until they have been ordered. ‘All materials in stock’ is therefore a dependency of ‘All materials ordered’.
‘Product manufactured’ is dependent on two nodes: ‘All materials in stock’ and ‘Equipment ready’.
All materials in stock
Equipment ready
Product complete
Start project
All materials ordered
Product manufactured

## Slide 7: Non-dependent tasks
A task may be included that is non-dependent. In this case it has no arrows to join it to the other nodes.
Here the annual review is included. It doesn’t matter when it is done but it will need slotting in somewhere.
All materials in stock
Equipment ready
Product complete
Start project
All materials ordered
Product manufactured
Annual review

## Slide 8: PERT as time management tool
Planners use PERT charts because they show the length of time a project will need.
All materials in stock
Equipment ready
Product complete
Start project
All materials ordered
Product manufactured
The number of days are shown on the diagram. In this example, it takes three days to get the equipment ready. There is a 20-day lead time on the materials arriving in stock.
1
1
3
20
10

## Slide 9: Identifying the critical path
Now the project planner can look at the chart and identify the critical path.
It only takes three days to get the equipment ready (on the bottom path) but it will take 22 days to get the materials into stock and ready for manufacturing (on the top path) (1 + 20 + 1).
All materials in stock
Equipment ready
Product complete
Start project
5 March 2022
All materials ordered
Product manufactured
20
10
1
1
3

## Slide 10: Critical paths and time management
So, the top path is the critical path. Nothing can be added to that path otherwise the project will take even longer.
However, extra tasks can be completed in any slack time (also known as ‘float’ time), represented by the bottom path once the equipment is ready.
All materials in stock
Equipment ready
Product complete
Start project
5 March 2022
All materials ordered
Product manufactured
20
10
1
1
3

## Slide 11: Working out the total time required
Stakeholders can be told that the whole project should take:
1 + 20 + 1 + 10 = 32 days.
However, from the manufacturer’s point of view it is also useful to know how long each individual task will take within this overall time frame.

## Slide 12: Estimating time frames
The PERT formula takes three estimates:
Optimistic time (O)
  The minimum amount of time needed to accomplish a task.
  For example, two days.
Pessimistic time (P)
  The maximum amount of time needed to accomplish a task.
  For example, four days.
Most likely time (M)
  The best estimate of how long it will take to accomplish a task.
  For example, three days.

## Slide 13: Calculating the best estimate
To calculate the best estimate, use the formula:
(O + (4 × M) + P) ÷ 6
So for the previous example:
(2 + (4 × 3) + 4) ÷ 6 = 3 days
Why not use the most likely time (M)? Many years of analysing projects has come up with this formula that builds in sufficient contingency and provides a more accurate result.

## Slide 14: Pros and cons of CPA
Advantages | Disadvantages
Provides a visual analysis of a project. | Needs some training/knowledge to create and interpret a CPA/PERT chart.
Very useful for planning time critical projects and estimating schedules. | Does not store much information about resources and staff.
Provides contingency with slack/float time in the schedule, reducing risk. | Complex projects can result in very large charts.
Easier to identify dependencies, reducing risks and helping to keep the project running to schedule. | 

## Slide 15
Any questions?
‘T-LEVELS’ is a registered trade mark of the Department for Education. ‘T Level’ is a registered trade mark of the Institute for Apprenticeships and Technical Education.