17. Project and programme management

# Worksheet 10: CPA (tutor)

- Describe the method of CPA.

CPA is a step-by-step project management technique used to identify activities on the critical path. It breaks a project down into work tasks in a flow chart, and calculates the project duration based on estimated time frames for each task.

- What does PERT stand for?

Project evaluation and review technique.

- What do the nodes and arrows on a PERT chart indicate?

Arrows represent the activities or work necessary to reach the events or nodes that indicate each completed phase of the project.

- List some of the advantage and disadvantages of CPA.

| Advantages | Disadvantages |
| --- | --- |
| Provides a visual analysis of a project. | Needs some training/knowledge to create and interpret a CPA/PERT chart. |
| Very useful for planning time critical projects and estimating schedules. | Does not store much information about resources and staff. |
| Provides contingency with slack/float time in the schedule, reducing risk. | Complex projects can result in very large charts. |
| Easier to identify dependencies, reducing risks and helping to keep the project running to schedule. |  |