5. Business

# Worksheet 15b: Project purpose statement (learner)

Below is a sample project plan for use in class.

Title of project: Farmers Markets Christmas Campaign 202X

Date: 28/02/2X

Project manager: Alex Addison

Project justification: Increase customer footfall to boost sales and attract new/more vendors to five Christmas Markets throughout Northeast England.

Project scope description: Create engaging full-scale marketing campaign for Christmas Markets to attract local and out-of-area visitors. Attract three high-profile sponsors.

Business objectives: Provide value to customers, increase footfall, boost sales, attract new vendors and encourage return of previous vendors.

Business deliverables:

- Draft content marketing plan for website and social media.

- Create competitive analysis and marketing strategy document.

- Gain budget approval from the Senior Management Team (SMT).

- Design brand campaign for adverts, print to be approved by Marketing Director to send to previous and potential vendors.

- Approach suitable high-profile organisations to offer gold/silver/bronze sponsorship options for marketing strength and budget support.

- Design full marketing campaign for online/offline marketing reach to potential customers, local visitors, national and international tourists.

- Farmers Market (vendors/sponsors) product gift hampers to be planned and collected to send to influencer team; delivery service to be booked.

Out of scope:

- Television advertisements

- Pay Per Click (PPC) campaign.

Constraints:

- Time constraints (six months until October launch dates for half term/tourist attractions).

- Small marketing team (three) with this project in addition to normal day-to-day work and requires substantial time.

- Delays in gathering products and delivering influencer gift hampers.

- Unknown additional costs.

Assumptions

- SMT will give approval for budget as outlined in the project proposal.

- Marketing manager will put together content marketing strategy and contribute to content creation.

- Event manager will allocate and organise layout and balance vendors at the Christmas Market events.

- Marketing director will approve Christmas Market campaign design and recruit sponsors.

- Marketing manager will assign team to put together influencer gift hampers and delivery. Top of Form